## 146
TMS CO 139-72 NE 13TH ST. BORES DAMAGED (MIAMI)
106002397
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| No Response, Current | AT T
| No Response, Current | HOTWIRE COMMUNICATIONS
| No Response, Current | CENTURYLINK
| No Response, Current | MCI
| No Response, Current | MIAMI-DADE WATER &amp; SEWER
| No Response, Current | CROWN CASTLE NG
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED. THIS LOCATE WAS NOT WHITE LINED.
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | CENTRAL SUPPORT FACILITY | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | COMCAST CABLE | 1: Marked
106002410
| No Response, Current | HOTWIRE COMMUNICATIONS
| No Response, Current | CENTURYLINK
| No Response, Current | MCI
| No Response, Current | MIAMI-DADE WATER &amp; SEWER
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/15 15:59 CONFLICT FPL AREA REFER TO TKT # 105006652 FOR PICTURES MARKED 04/15 FOR SAME CONTRACTOR 04/15
| Current | FLORIDA GAS TRANSMISSION | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | CENTRAL SUPPORT FACILITY | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area

## 145
TMS PROJECT ID 251688-1-52-01 (MIAMI)
105006641
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| No Response, Current | TRAFFIC MANAGEMENT SOLUTIONS
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ANY QUESTIONS CALL STEVE AT (305) 797-8459. OPERATION HRS. TO CALL, M-F 6AM TO 2:30 PM. ON SITE MEET REQUIRED TO REVIEW FPL TRANSMISSION AS-BUILT 24HR PRIOR TO EXCAVATION OR DIRECT BORING CONTACT STEVE (305) 797-8459 TO SCHEDULE A MEET, OPERATION HR. TO CALL M-F 6:00 AM-2:30PM.
| Current | AT T | 1: Marked | NULL
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | CENTRAL SUPPORT FACILITY | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | MASTEC INC | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/16 15:48 CONFLICT REFER TO TKT # 105004817 FOR PICTURES. MARKED FOR " NEW ERA ELECTRIC INC " 04/16
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 3T: Extraordinary circumstances per 556.105(8)(a), F.S. exist, call utility owner / operator provider for this location.
| Current | CENTURYLINK | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
105006644
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | AT T | 3T: Extraordinary circumstances per 556.105(8)(a), F.S. exist, call utility owner / operator provider for this location. | NULL
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | CENTRAL SUPPORT FACILITY | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 3N: Unmarked - Locate description is insufficient - white lining is required per 556.114(3), FS Please contact the utility when the white lining is completed.
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 3T: Extraordinary circumstances per 556.105(8)(a), F.S. exist, call utility owner / operator provider for this location.
| Current | CENTURYLINK | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
105006647
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| No Response, Current | MASTEC INC
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | FLORIDA GAS TRANSMISSION | 5: No Conflict - utility is outside of the requested work site
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | CENTRAL SUPPORT FACILITY | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/15 15:24 CONFLICT FPL AREA
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 3T: Extraordinary circumstances per 556.105(8)(a), F.S. exist, call utility owner / operator provider for this location.
| Current | CENTURYLINK | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
105006652
| No Response, Current | MASTEC INC
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | FLORIDA GAS TRANSMISSION | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | CENTRAL SUPPORT FACILITY | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | MCI | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/15 15:45 CONFLICT,TWO RUN FOR ATT/D FACILITIES FPL AREA.
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 5: No Conflict - utility is outside of the requested work site
| Current | CENTURYLINK | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
106002314
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| No Response, Current | CENTURYLINK
| No Response, Current | MASTEC INC
| No Response, Current | MCI
| No Response, Current | TECO PEOPLES GAS SOUTH FLORIDA
| No Response, Current | TRAFFIC MANAGEMENT SOLUTIONS
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ANY QUESTIONS CALL STEVE AT (305) 797-8459. OPERATION HRS. TO CALL, M-F 6AM TO 2:30 PM.
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | AT T | 1: Marked | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | CENTRAL SUPPORT FACILITY | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/17 08:24 CONFLICT,REFER TO TKT # 105004817 MARKED FOR "NEW ERA ELECTRIC INC " 04/16.
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 144
BLUE STREAK - 02A46030N (HOLLYWOOD)
105005088
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BROWARD COUNTY WATER AND WASTEWATER SERVICES | 4: Clear No Facilities
| Current | CITY OF HOLLYWOOD, PUBLIC WORKS DEPARTMENT | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities

## 143
QUANTA S236346 (DORAL) NW 41ST ST / NW 87TH AVE
105002188
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| No Response, Current | MASTEC INC
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | UNIVISION NETWORK | 4: Clear No Facilities
| Current | FLORIDA CITY GAS | 3N: Unmarked - Locate description is insufficient - white lining is required per 556.114(3), FS Please contact the utility when the white lining is completed.
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | COMCAST CABLE | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/16 14:30 LOCATED 3 OUT OF 5 SPOKE TO CONTACT ON SITE, HE WILL START ON TICKET 4 WORKING WEST TO THIS TICKET, WHICH IS THE 5TH ONE HE AGREED ON DELAY, AND I WILL COMPLETE IT TOMORROW OR SATURDAY 105002234
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
105002234
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| No Response, Current | MASTEC INC
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | UNIVISION NETWORK | 4: Clear No Facilities
| Current | FLORIDA CITY GAS | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | MCI | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | A T &amp; T/ DISTRIBUTION | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/16 14:15 LOCATED 3 OUT OF 4 SPOKE TO CONTACT ON SITE, HE WILL START ON TICKET 4 WORKING WEST TO THIS TICKET, #1 HE AGREED ON DELAY, AND I WILL COMPLETE IT TOMORROW OR SATURDAY 105002234
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
105002251
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | UNIVISION NETWORK | 4: Clear No Facilities
| Current | FLORIDA CITY GAS | 1: Marked
| Current | MCI | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
105002260
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | UNIVISION NETWORK | 4: Clear No Facilities
| Current | FLORIDA CITY GAS | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
105002301
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | UNIVISION NETWORK | 4: Clear No Facilities
| Current | FLORIDA CITY GAS | 1: Marked
| Current | MCI | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear

## 142
BLUE STREAK - 9EA02912N (WESTON) FALCON COVE MIDDLE SCHOOL
100006790
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MASTEC INC | 4: Clear No Facilities
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 4: Clear No Facilities
| Current | CITY OF PEMBROKE PINES / CH2M | 3U: Unmarked - Not service provider for this location
| Current | CITY OF WESTON - FIBER OPTIC | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF WESTON- ELECTRIC | 1: Marked
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 4: Clear No Facilities
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
| Current | ADVANCED CABLE COMMUNICATIONS | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/13 18:07 DEAR 811 LOCATE RECIPIENT, USIC LOCATING SERVICES 3337 NW 55TH STREET FORT LAUDERDALE, FL 33309 811 CALL BEFORE YOU DIG THIS EMAIL IS TO DELAY THE LOCATE TICKET #100006790/100006794/100006798. THIS IS CONSIDERED A POSITIVE RESPONSE EMAIL ACKNOWLEDGING THE LOCATE TICKET REQUESTED ABOVE TO BE DELAYED DUE TO IN-FIELD SCHEDULING. IF YOU ARE GOING TO BE ONSITE WITHIN THE NEXT 12-24 HOURS REPLY ALL TO THE EMAIL AND/OR CALL THE NUMBER BELOW. IF THERE IS A HOLIDAY THEN PLEASE ADD A BUSINESS DAY. COMPLETING THE LOCATE TICKET ON TIME AND MARKING IT CORRECTLY IS OUR TOP PRIORITY AND WE WANT TO ENSURE THAT YOU ARE SATISFIED WITH OUR WORK. IF THERE ARE ANY ISSUES THAT ARISE IN BETWEEN THE TIME YOU HAVE READ THIS EMAIL TO THE TIME YOUR LOCATE TICKET IS COMPLETED PLEASE CALL THE USIC DISPATCH LINE @ 317-575-7800 AND PRESS OPT 1. PLEASE NOTE THAT THIS IS THE POSITIVE RESPONSE DELAYING THE LOCATE TICKET. SINCERELY, GEORGE RODRIGUEZ 954-240-4009 USIC LOCATING SERVICES-
100006794
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 4: Clear No Facilities
| Current | CITY OF PEMBROKE PINES / CH2M | 3U: Unmarked - Not service provider for this location
| Current | CITY OF WESTON- ELECTRIC | 1: Marked
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
| Current | ADVANCED CABLE COMMUNICATIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/13 18:07 DEAR 811 LOCATE RECIPIENT, USIC LOCATING SERVICES 3337 NW 55TH STREET FORT LAUDERDALE, FL 33309 811 CALL BEFORE YOU DIG THIS EMAIL IS TO DELAY THE LOCATE TICKET #100006790/100006794/100006798. THIS IS CONSIDERED A POSITIVE RESPONSE EMAIL ACKNOWLEDGING THE LOCATE TICKET REQUESTED ABOVE TO BE DELAYED DUE TO IN-FIELD SCHEDULING. IF YOU ARE GOING TO BE ONSITE WITHIN THE NEXT 12-24 HOURS REPLY ALL TO THE EMAIL AND/OR CALL THE NUMBER BELOW. IF THERE IS A HOLIDAY THEN PLEASE ADD A BUSINESS DAY. COMPLETING THE LOCATE TICKET ON TIME AND MARKING IT CORRECTLY IS OUR TOP PRIORITY AND WE WANT TO ENSURE THAT YOU ARE SATISFIED WITH OUR WORK. IF THERE ARE ANY ISSUES THAT ARISE IN BETWEEN THE TIME YOU HAVE READ THIS EMAIL TO THE TIME YOUR LOCATE TICKET IS COMPLETED PLEASE CALL THE USIC DISPATCH LINE @ 317-575-7800 AND PRESS OPT 1. PLEASE NOTE THAT THIS IS THE POSITIVE RESPONSE DELAYING THE LOCATE TICKET. SINCERELY, GEORGE RODRIGUEZ 954-240-4009 USIC LOCATING SERVICES-
100006798
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 4: Clear No Facilities
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON | 1: Marked
| Current | CITY OF PEMBROKE PINES / CH2M | 3U: Unmarked - Not service provider for this location
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | ADVANCED CABLE COMMUNICATIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/13 18:07 DEAR 811 LOCATE RECIPIENT, USIC LOCATING SERVICES 3337 NW 55TH STREET FORT LAUDERDALE, FL 33309 811 CALL BEFORE YOU DIG THIS EMAIL IS TO DELAY THE LOCATE TICKET #100006790/100006794/100006798. THIS IS CONSIDERED A POSITIVE RESPONSE EMAIL ACKNOWLEDGING THE LOCATE TICKET REQUESTED ABOVE TO BE DELAYED DUE TO IN-FIELD SCHEDULING. IF YOU ARE GOING TO BE ONSITE WITHIN THE NEXT 12-24 HOURS REPLY ALL TO THE EMAIL AND/OR CALL THE NUMBER BELOW. IF THERE IS A HOLIDAY THEN PLEASE ADD A BUSINESS DAY. COMPLETING THE LOCATE TICKET ON TIME AND MARKING IT CORRECTLY IS OUR TOP PRIORITY AND WE WANT TO ENSURE THAT YOU ARE SATISFIED WITH OUR WORK. IF THERE ARE ANY ISSUES THAT ARISE IN BETWEEN THE TIME YOU HAVE READ THIS EMAIL TO THE TIME YOUR LOCATE TICKET IS COMPLETED PLEASE CALL THE USIC DISPATCH LINE @ 317-575-7800 AND PRESS OPT 1. PLEASE NOTE THAT THIS IS THE POSITIVE RESPONSE DELAYING THE LOCATE TICKET. SINCERELY, GEORGE RODRIGUEZ 954-240-4009 USIC LOCATING SERVICES-

## 141
BLUE STREAK - 9EA31119A (PLANTATION) BY THE CENTER FOR JEWISH LIFE W BROWARD BLVD
100001851
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CROWN CASTLE NG | 1: Marked
| Current | CITY OF SUNRISE GAS | 4: Clear No Facilities
| Current | CITY OF PLANTATION UTILITIES DEPARTMENT | 2D: Marked with Exceptions - High Profile utility in conflict
| Current | HOTWIRE COMMUNICATIONS | 1: Marked
| Current | CITY OF SUNRISE WATER &amp; WASTEWATER DEPARTMENT | 4: Clear No Facilities
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement. | 2020/04/13 18:01 ADVISED CESAR LOCATE WILL BE COMPLETED BY, 04/14/20 4:00 P.M.
| Current | CENTURYLINK | 1: Marked

## 140
BLUE STREAK - 9EA02904N (WESTON) S POST RD
106002947
| No Response, Current | BROWARD COUNTY TRAFFIC ENGINEERING
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MASTEC INC | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | ADVANCED CABLE COMMUNICATIONS | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/16 09:47 FACILITIES MARKED FOLLOW FLAGS AND PAINT, REFER TO PICS. BE ADVISED NO DETAILED PRINTS FOR ADVANCED CABLE, VERIFIED ON SITE. 106002947
| Current | CITY OF WESTON- ELECTRIC | 1: Marked
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON - FIBER OPTIC | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF WESTON | 1: Marked
106002956
| No Response, Current | BROWARD COUNTY TRAFFIC ENGINEERING
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MASTEC INC | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | ADVANCED CABLE COMMUNICATIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/16 09:48 FACILITIES MARKED FOLLOW FLAGS AND PAINT, REFER TO PICS. BE ADVISED NO DETAILED PRINTS FOR ADVANCED CABLE, VERIFIED ON SITE. 106002947
| Current | CITY OF WESTON- ELECTRIC | 1: Marked
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON - FIBER OPTIC | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF WESTON | 1: Marked
NOTE: ORIGINAL TICKET 100001577 IS CLEAR

## 139
BLUE STREAK - 9EA11148N (MIRAMAR) RED RD BY TURNPIKE
099007318
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | BUCKEYE PIPELINE CO | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF MIRAMAR | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
| Current | FLORIDA CITY GAS | 1: Marked
100000002
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BUCKEYE PIPELINE CO | 5: No Conflict - utility is outside of the requested work site
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
| Current | FLORIDA CITY GAS | 1: Marked
| Current | CITY OF MIRAMAR | 1: Marked
100000006
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BUCKEYE PIPELINE CO | 5: No Conflict - utility is outside of the requested work site
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF MIRAMAR | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
| Current | FLORIDA CITY GAS | 5: No Conflict - utility is outside of the requested work site

## 138
QUANTA CCF20285855 (LAKE WORTH) Damaged Handhole
098002672
| No Response, Current | MASTEC INC
| Current | PALM BEACH COUNTY TRAFFIC OPERATIONS | 4: Clear No Facilities
| Current | FLA PUBLIC UTILITIES CO | 4: Clear No Facilities | CLEAR PER FPU PRINT
| Current | CITY OF ATLANTIS | 3U: Unmarked - Not service provider for this location
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | COMCAST-PBG | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | CITY OF LAKE WORTH - ELECTRIC DEPARTMENT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - PALM BEACH | 4: Clear No Facilities | 2020/04/09 15:08 CALLED AND INFORMED CESAR ON 4/9/20 THAT I WILL BE RESCHEDULING THIS TICKET AND IT WILL BE COMPLETED 4/11/20 BY 5PM. 2020/04/10 16:08 CALLED AND INFORMED CESAR ON 4/9/20 THAT I WILL BE RESCHEDULING THIS TICKET AND IT WILL BE COMPLETED 4/11/20 BY 5PM. 2020/04/13 12:00 SEE TICKET 098002689 FOR PICTURES/ DETAILS
098002680
| No Response, Current | MASTEC INC
| Current | PALM BEACH COUNTY TRAFFIC OPERATIONS | 4: Clear No Facilities
| Current | FLA PUBLIC UTILITIES CO | 4: Clear No Facilities | CLEAR PER FPU PRINT
| Current | CITY OF ATLANTIS | 3U: Unmarked - Not service provider for this location
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST-PBG | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | CITY OF LAKE WORTH - ELECTRIC DEPARTMENT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - PALM BEACH | 4: Clear No Facilities | 2020/04/09 15:08 CALLED AND INFORMED CESAR ON 4/9/20 THAT I WILL BE RESCHEDULING THIS TICKET AND IT WILL BE COMPLETED 4/11/20 BY 5PM. 2020/04/10 16:08 CALLED AND INFORMED CESAR ON 4/9/20 THAT I WILL BE RESCHEDULING THIS TICKET AND IT WILL BE COMPLETED 4/11/20 BY 5PM. 2020/04/13 11:59 SEE TICKET 098002689 FOR PICTURES/ DETAILS
098002689
| No Response, Current | MASTEC INC
| Current | PALM BEACH COUNTY TRAFFIC OPERATIONS | 4: Clear No Facilities
| Current | FLA PUBLIC UTILITIES CO | 4: Clear No Facilities | CLEAR PER FPU PRINT
| Current | CITY OF ATLANTIS | 3U: Unmarked - Not service provider for this location
| Current | MCI | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | COMCAST-PBG | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | CITY OF LAKE WORTH - ELECTRIC DEPARTMENT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - PALM BEACH | 4: Clear No Facilities | 2020/04/09 15:09 CALLED AND INFORMED CESAR ON 4/9/20 THAT I WILL BE RESCHEDULING THIS TICKET AND IT WILL BE COMPLETED 4/11/20 BY 5PM. 2020/04/10 16:09 CALLED AND INFORMED CESAR ON 4/9/20 THAT I WILL BE RESCHEDULING THIS TICKET AND IT WILL BE COMPLETED 4/11/20 BY 5PM. 2020/04/13 11:58 PAINT AND FLAG CATV, ATT....SEE PICTURES FPL, WATER, SEWER....CLEAR

## 137
BLUE STREAK - 02A75070N (HOLLYWOOD) 1805 PIERCE ST CHURCH
096000203
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MCI | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | MASTEC INC | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities
| Current | WINDSTREAM COMMUNICATION | 1: Marked
| Current | CITY OF HOLLYWOOD PUBLIC UTILITIES DEPT | 1: Marked | GPR-R LOCATING USED.
| Current | CITY OF HOLLYWOOD, PUBLIC WORKS DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
096000207
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | WINDSTREAM COMMUNICATION | 4: Clear No Facilities
| Current | MASTEC INC | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
| Current | CITY OF HOLLYWOOD PUBLIC UTILITIES DEPT | 1: Marked | GPR-R LOCATING USED.
| Current | CITY OF HOLLYWOOD, PUBLIC WORKS DEPARTMENT | 1: Marked | OFFSETS USED IN LOCATE.
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area

## 133
BLUE STREAK - 9EA3IIO8N (PLANTATION) W SUNRISE BLVD / LAUDERDALE W DR
092005596
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF SUNRISE GAS | 4: Clear No Facilities
| Current | CITY OF PLANTATION UTILITIES DEPARTMENT | 1: Marked
| Current | CITY OF SUNRISE WATER &amp; WASTEWATER DEPARTMENT | 4: Clear No Facilities
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | MASTEC INC | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.

## 130
BLUE STREAK - 02A65023N (DEERFIELD BEACH) E SAMPLE RD
090007362
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF POMPANO BEACH WATER/SEWER | 3U: Unmarked - Not service provider for this location
| Current | CITY OF DEERFIELD BEACH | 3U: Unmarked - Not service provider for this location
| Current | SPRINT | 1: Marked
| Current | MCI | 4: Clear No Facilities
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 4: Clear No Facilities
| Current | BROWARD COUNTY WATER AND WASTEWATER SERVICES | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities

## 129
BLUE STREAK - Permit# 2019-230-TL (PARKLAND) Fire Station 109 W HILLSBORO BLVD
090007341
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/01 14:42 TALKED TO MIKE THEY STARTED TODAY I WILL DO FIRST THING TOMORROW
090007344
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
090007345
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
090007347
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
090007348
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked

## 128
BLUE STREAK - 02A25098B (FT LAUD) Convention Center
090007307
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MCI | 4: Clear No Facilities
| Current | TRANSMONTAIGNE PRODUCT SERVICES INC FKA C F M | 4: Clear No Facilities
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | BUCKEYE PIPELINE CO | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | EXXON MOBIL PIPELINE CO. | 4: Clear No Facilities
| Current | CITY OF HOLLYWOOD, PUBLIC WORKS DEPARTMENT | 3U: Unmarked - Not service provider for this location
| Current | BROWARD COUNTY PORT EVERGLADES DEPT | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
| Current | MPLX TERMINALS LLC | 1: Marked

## 127
BLUE STREAK - 02A5905ON (PARKLAND) W HILLSBORO BLVD &amp; NOB HILL RD
087002597
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MCI | 4: Clear No Facilities
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
087002606
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MCI | 4: Clear No Facilities
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 2E: Marked with Exceptions - Marked within the confines of white-lined area
087002614
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MCI | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 2E: Marked with Exceptions - Marked within the confines of white-lined area

## 125
BLUE STREAK - 9EA72069A (SUNRISE) 12590 W SUNRISE BLVD (CHASE BANK)
086003974
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF SUNRISE GAS | 4: Clear No Facilities
| Current | CITY OF SUNRISE WATER &amp; WASTEWATER DEPARTMENT | 1: Marked
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | MASTEC INC | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/03/30 15:51 ADVISED MICHAEL WILLIAMS LOCATE WILL BE COMPLETED BY, 04/06/20 4:00 P.M.

## 123
BLUE STREAK - 0EA72094A (SUNRISE) SUNRISE BLVD
086000181
| Current | CITY OF SUNRISE GAS | 1: Marked
| Current | CITY OF SUNRISE WATER &amp; WASTEWATER DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | MASTEC INC | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/03/30 15:45 ADVISED MICHAEL WILLIAMS LOCATE WILL BE COMPLETED BY, 04/06/20 4:00 P.M. 2020/03/31 10:49 CONTRACTOR'S URGENT REQUEST FOR IMMEDIATE ATTENTION NOW! I SPOKE WITH MIKE WILLIAMS PHONE: 954-599-1947 AT 10:46AM ON 03\31\20 REGARDING TICKET# 086000181 AT W SUNRISE BLVD &amp; NW 143RD AVE, SUNRISE, FL. HE CURRENTLY HAS CREW ON SITE AWAITING LOCATES TO BE COMPLETED IMMEDIATELY TODAY BECAUSE EXCAVATION MUST START THIS MORNING. THIS IS AN URGENT AT&amp;T PROJECT. PLEASE CONTACT MIKE WILLIAMS PHONE: 954-599-1947 WITH STATUS AS SOON AS POSSIBLE THIS MORNING. CONFIRMATION EMAIL SENT TO FIBER1COMMUNICATIONS@GMAIL.COM 2020/03/31 11:15 WORK DONE FOR ATT/BLUE STREAK. LOCATES OWN FACILITIES.

## 116
BLUE STREAK - 02A25085N FT LAUD (SE 9TH ST)
076007085
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | WINDSTREAM COMMUNICATION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CITY OF FT LAUDERDALE | 1: Marked
076007087
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | WINDSTREAM COMMUNICATION | 1: Marked
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | CENTURYLINK | 1: Marked

## 111
BLUE STREAK - 9EA25101D (FT LAUD) Las Olas 3x4"
062007665
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked | AS 2020-0305 388-400 NUMBER OF UNITS: 2.
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked

## 107
CROWN CASTLE - 6MD1139C-HUB (Miami)
045001744
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MCI | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/03/03 09:44 MARKED ALREADY.....
| Current | FLORIDA CITY GAS | 2C: Marked with Exceptions - High priority subsurface installation in conflict. Excavator MUST notify the member of the excavation or demolition start date and time. See s.556.116(1) and (2), F.S.
045001819
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MCI | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 4: Clear No Facilities
| Current | FLORIDA GAS TRANSMISSION | 2C: Marked with Exceptions - High priority subsurface installation in conflict. Excavator MUST notify the member of the excavation or demolition start date and time. See s.556.116(1) and (2), F.S.
| Current | FLORIDA CITY GAS | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked